## Slide 1: CHAPTER – 3 PROJECT IMPLEMENTATION PROCEDURES
NIRD & PR

## Slide 2
Chapter- 1
Introduction
Chapter-3
Project Implementation Procedures
Training
Chapter – 5
Training Centre
Chapter- 6
Training Initiation
Chapter-4
Training Design & Planning
Standard Operating Procedures
Chapter 7 – Tracking & Placement
Chapter 8 – Project Financial Management
Chapter 9 – Grading of a project &Project implementing Agency

## Slide 3: Outline of Chapter 3
MoU Execution
Preparatory work for execution of MoU
Project Commencement
Project execution readiness assessment
Instalments
1st, 2nd, 3rd and 4th
Completion
Completion of training and placement
Others
Signing of MoU
Project commencement order
Closure of the project
Consortium arrangements & Outsourcing of activities
Orderly closure
Project manpower plan
Recovery of dues from a PIA

## Slide 4: 3.1 MoU execution (page 15)
Item | Description
Purpose | To lay down MoU execution process and related timelines
Reference to Guidelines | Step 6 & 7, table 4, Para 4.1, page 36 and 46
Prerequisite/s | Uploading of approved empowered committee (EC) minutes and sanction order
Time for completion | 20 working days from uploading of sanction order on the nominated website (Sanction order uploading day is referred as ‘I2’)
Resource/s | As per SF 3.1A: Prospective project work schedule (live demo in ASDMS), SF 3.1B: Standard terms & conditions, 3.1.1C: Special terms & conditions and 3.1.1D: Power of Attorney (PoA)
Process owner | For AAP States: SRLM For non AAP states: CTSA

## Slide 5
Item | Description
Purpose | To delineate the preparatory work for MoU execution and related timelines
Prerequisite/s | Uploading of EC minutes on the nominated website
Time for completion | 15 days of time gap between I1 & I2 and 2 days after I2 (I1: Uploading of approved EC minutes and I2: Uploading of Sanction order)
Resource/s | As per SF 3.1A: Prospective project work schedule, SF 3.1B: Standard terms & condition, 3.1.1C: Special terms & conditions and 3.1.1D: Power of Attorney (PoA)
Process owner | For AAP States: SRLM For non AAP states: CTSA

## Slide 6: 3.1.1.1 Prospective work schedule of the project: contents and relevance (page 16
Prospective work schedule includes the following
  Monthly training commencement schedule for the complete project duration
  Monthly training completion schedule for the complete project duration
  First batch of training has to be commenced within 90 days of Project commencement date
  minimum training to be commenced in each year for the different time duration of projects
Project duration | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
<= 1 year | 100% |  |  |  |  | 100%
<= 2 year | 35% | 65% |  |  |  | 100%
<= 3 year | 30% | 35% | 35% |  |  | 100%
<= 4 year | 20% | 20% | 35% | 25% |  | 100%
<= 5 year | 15% | 25% | 20% | 25% | 15% | 100%

## Slide 7: 3.1.1.2 Monitoring of the prospective work schedule and penal clauses for failure (page 18)
PIA has to report following on monthly basis
  Training commenced by the month once the batch is frozen
  Training completion by the month once the batch is completed
Validation on cumulative achievement of monthly target
* Not applicable for 1 year project
Project phase | Tolerance level of shortfall
First 6 months | Up to 10%
From 7th month to till 6 months before completion | Up to 5%*
Last 6 months | Nil

## Slide 8: Continued
Any shortfall in achievement of cumulative monthly target will trigger the following notices
Notice no. | Notice type | PIA representative need to be attended
1 | Yellow alert | Project head, SRLM and CTSA representatives
2 | Red alert | Authorised signatory along with Project head, SRLM and CTSA representatives
3 | Notice of default | CEO or equivalent along with Authorised signatory and Project head, SRLM and CTSA representatives
4 | Termination of the project | CEO or equivalent along with Authorised signatory and Project head, SRLM and CTSA representatives

## Slide 9: Continued
Timelines for review
  All notices which are not closed will be counted cumulatively and third unclosed notice will lead to action under default
  In case of absence or if the representation is not as per the level specified it will be treated as a separate default and action under the section on remedy for default will be invoked
  After issue of a notice under default (i.e. after issue of yellow and red alerts) any shortfall in cumulative totals will lead to issue of notices under default directly
Sl. | Event | Time for completion
1 | Issue of notice | By 8th of the following month
2 | Reply of PIA | By 13th of the following month
3 | Meeting at MoRD | On 3rd Monday of the following month

## Slide 10: 3.1.2 Signing of MoU (page 19)
Item | Description
Purpose | To delineate the steps/actions to be taken in signing MoU
Prerequisite/s | Uploading of sanction order on the nominated website
Time for completion | 20 working days from uploading of sanction order (start from I2 day)
Resource/s | MoU
Process owner | For AAP States: SRLM For non AAP states: CTSA

## Slide 11: 3.2 Release of 1st instalment (page 22)
Item | Description
Purpose | To lay down the fund release process for 1st instalment and issue of Project commencement order to PIA
Reference to Guidelines | Row 1, Instalment 1, table 6, para 5.9, page 56
Prerequisite/s | Uploading of executed MoU
Time for completion | 10 working days after signing the MoU (MoU execution day is coded as I3)
Resource/s | As per SF 3.2A: Bank account details (page 36) and SF 3.2B: Project commencement order (page 37)
Process owner: | For AAP States: SRLM For Non-AAP States: CTSA

## Slide 12: 3.3 Project execution readiness assessment (page 23)
Item | Description
Purpose | To ensure availability of basic core team for implementing the project and sensitize them in implementation procedures
Reference to Guidelines | NA
Prerequisite/s | Uploading of sanction order on the designated website
Time for completion | Any time after issue of sanction order but not later than 30 days from release of 1st Instalment (not later than I4­ +30)
Resource/s | SF 3.3A: Project execution readiness assessment form (page 38)
Process owner | PIA for all states

## Slide 13: 3.4 Release of 2nd instalment (page 23)
Item | Description
Purpose | To specify activities for release of 2nd instalment of funds to PIA
Reference to Guidelines | Row 2, instalment 2, table 6, para 5.9, page 56
Prerequisite/s | System generated notification for fulfilment of condition as per above reference to guidelines
Time for completion | 60 working days for non AAP states (40 working days for AAP states) from eligibility day (notification date of eligibility for 2nd instalment is coded as E2) provided all conditions are fulfilled by the PIA.
Resource/s | SF 3.4A: Checklist for release of 2nd instalment updated through the system (accessed from the web-link)
Process owner | for AAP States: SRLM for Non-AAP States 1) CTSA till dispatch of recommendation to MoRD and also for release of funds after MoRD issues release order 2) MoRD after receipt of recommendation and till issue of release order

## Slide 14: 3.5 Release of 3rd instalment (page 24)
Item | Description
Purpose | To delineate steps in release of 3rd instalment to PIA
Reference to Guidelines | Row 3, instalment 3, table 6, para 5.9, page 56
Prerequisite/s | System generated notification for fulfilment of condition as per above reference to guidelines
Time for completion | 60 working days for non AAP states (40 working days for AAP states) from eligibility day (notification date of eligibility for 3nd instalment is referred as ‘E4’ day) provided all conditions are fulfilled by the PIA.
Resource/s | SF 3.5A: Checklist for release of 3rd instalment
Process owner | for AAP States: SRLM for Non-AAP States 1) CTSA till dispatch of recommendation to MoRD and also for release of funds after MoRD issues release order. 2) MoRD after receipt of recommendation and till issue of release order

## Slide 15: 3.6 Completion of training and placement (page 26)
Item | Description
Purpose | To verify and close the training and placement component of the project
Reference to Guidelines | NA
Prerequisite/s | Completion of project training and placement activities
Time for completion | Complete within 70 days after the PIA completes the project training and placement process. (Date of completion of placement for the project is referred as ‘E7’ day).
Resource/s | SF 3.7B Project completion report
Process owner | For AAP States: SRLM/For Non-AAP States: CTSA

## Slide 16: 3.7 Release of 4th instalment and closure of project (page 27)
Item | Description
Purpose | To lay down the fund release process of 4th instalment to PIA & closure of the project
Reference to Guidelines | Row 4, instalment 4, table 6, para 5.9, page 56
Prerequisite/s | Fulfilment of condition as per reference to guidelines and notification for data freezing on the web-link
Time for completion | 14 months from ‘E7’ day
Resource/s | SF 3.7A: Checklist for release of 4th instalment and SF 3.7B Project completion report
Process owner | SRLM for AAP States/CTSA for Non-AAP States

## Slide 17: 3.8 Consortium agreement and Outsourcing of activities (page 28)
Consortium
  All the partners are jointly and severally responsible for the project
  In case of default of any partner the lead partner has to inform SRLM for AAP states and CTSA for Non AAP states within 10 days of the default
  Undertake the task assigned to defaulting members by the lead partner directly or through any of the consortium partners and the same to be informed
  Failure to comply with this condition will lead to termination of the project
Outsourcing
  In case of failure, PIA should undertake the activity directly
  Change of outsourcing partners are not allowed
  For outsourcing of activities other than training and placement, PIA has to inform within 10 days before commencement of the activity
  Contd…

## Slide 18: Continued
  The information has to be contained with name of outsourcing partner, financial and legal terms of arrangement
  In case of default by outsourcing partners, PIA has to take up the activity by himself
  The financial transactions will be transparent and done through PFMS. Till such time PFMS is in place all transactions between various agencies in the project should be done through the banking system only
  If these conditions are not met, a PIA is deemed to have defaulted and action can be initiated as per the rules.

## Slide 19: 3.9 orderly closure of a project (page 29)
A project can be closed/terminated under the following conditions:
When a PIA is:
  Under conditions of default
  unable to execute the project
  unable to abide by modifications incorporated in guidelines and SOP
  Under any other condition not envisaged above

## Slide 20: 3.10 Project manpower plan (page 30)
  The management (including Q team head)
  Operations team and
  Q team
Ring fencing of ‘Q’ team from operations (SF 3.10C) (page 46)
  The Q team head will report to the management and not to the project operations head
  Q team members will report only to the Q team head
Contd…

## Slide 21: Continued
  Appointments should be regulated such that:
    No Q team members should be posted to the OP team of the same project within 15 months of completing the Q team assignment and vice versa
    Movement within the Q team and to OP team of other projects is permitted
    All changes in Q team should be brought to the notice CTSA/SRLM
      All planned changes should be informed 15 days before
      Unplanned changes should be reported immediately within 48 hours
    Any deviation from this will be treated as violation and will be reflected in the PIA grading
Contd…

## Slide 22: Continued
    The salary and structure of Q team should not be changed to Q members disadvantage without approval of CTSA/SRLM
    Performance appraisals of the Q team should be sent to the CTSA /SRLM
    Performance of Q team will be reviewed by CTSA/SRLM along with the management whenever required by CTSA/SRLM
Contd…

## Slide 23: 3.11 Recovery of dues from a PIA (page 30)
If the PIA fails to repay the amount it is necessary to invoke the revenue recovery act 1890 or other applicable Revenue Recovery or Public Demands Recovery Act of the state/UT.
Contd…

## Slide 24: Continued
The procedure to recover the Government dues is as follows:
All SRLMs, i.e. both AAP and non AAP states, should issue procedural orders on how the recovery would be made as per the relevant act in the state
All efforts will be made to recover the money from the PIA by SRLMs in case of AAP states and by MoRD through the CTSA for non AAP states
If all efforts to recover the dues fail the procedural order for recovery of dues will be invoked by:
  SRLM in case of AAP states with information to MoRD
  SRLM on the recommendation of MoRD in case of non AAP states
MoRD will maintain a list of such PIAs and also circulate the same to all SRLMs and CTSAs. This would also be updated on the designated website

## Slide 25
THANKYOU