## Slide 1: Chapter – 4 Training Design & Planning
NIRD & PR

## Slide 2
Chapter- 1
Introduction
Chapter-3
Project Implementation Procedures
Training
Chapter – 5
Training Centre
Chapter- 6
Training Initiation
Chapter-4
Training Design & Planning
Standard Operating Procedures
Chapter 7 – Tracking & Placement
Chapter 8 – Project Financial Management
Chapter 9 – Grading of a project &Project implementing Agency

## Slide 3: Outline of Chapter 4
Planner
Training Plan
Curriculum
Domain Curriculum
Assessment & Certification
Outline of assessment and certifying
Activity cum lesson Planner
Non - Domain Curriculum
Others
Finishing and Work readiness module
OJT plan
Protocol for managing tablets and electronic content
Distance education using live studio based broadcasts

## Slide 4: 4.1 Training plan (1/2)
Item` | Description
Purpose | To create an aggregate distribution plan between classroom and on job training for both domain and non-domain skills.
Reference to guidelines | Para 3.2.2.2.3, page-29
Prerequisite/s | Any time after uploading of Sanction order and 15 days before commencement of training in the particular trade
Time for completion | 15 days before commencement of training in the particular trade
Resource/s | SOP- SF 4.1 A: Plan of Training (Page No- 58)
Process owner | PIA OP team

## Slide 5: 4.1 Training plan (2/2)
Item` | Description
Training Plan | Should match with daily training hours as indicated in the application form
Residential Courses | Mandatorily to be held for 8 hours / day Boarding & Lodging charges will be paid for entire duration of stay (including holidays)
Non - residential Courses | Training hours is flexible provided it is indicated in the application form and duly approved by the Empowered Committee. To and fro charges and food will be paid at Rs. 100 for every 8 hours of training.

## Slide 6: 4.2 Domain curriculum
Item` | Description
Purpose | To ensure that the domain curriculum is: As per the module prescribed by NCVT Either aligned as per SSC prescribed NOS-QP module or the proposed module has prior approval of SSC
Reference to guidelines | Para 3.2.2.2.3, page-29
Prerequisite/s | Any time after uploading of Sanction order and 15 days before commencement of training in the particular trade
Time for completion | 15 days before commencement of training in the particular trade
Resource/s | SOP- SF 4.2 A: Domain Curriculum (Page No- 59)
Process owner | PIA OP team

## Slide 7: 4.3 Non-Domain curriculum
Item` | Description
Purpose | To develop uniform standards for curriculum for Soft Skills, Computer Skills and English Skills
Reference to guidelines | Para 3.2.2.2.3, page-29
Prerequisite/s | Any time after uploading of Sanction order and 15 days before commencement of training in the particular trade
Time for completion | 15 days before commencement of training in the particular trade
Resource/s | SOP- SF 4.3 A: English Skills Content (Page No- 60 to 62) SOP- SF 4.3 B: Computer Skills Content (Page No- 63 to 64) SOP- SF 4.3 A: Soft Skills Content (Page No- 65 to 68)
Process owner | PIA OP team

## Slide 8: 4.4 Finishing and work readiness module
Item | Description
Purpose | To ensure high rate of success in placement and retention
Reference to guidelines | Para 3.2.2.2.5, page – 29
Prerequisite/s | Any time after uploading of Sanction order and 15 days before start of training
Time for completion | 15 days before initiation of first training
Resource/s | SOP – SF 4.4 A: Finishing and work readiness module (Page no- 69)
Process owner | PIA OP team

## Slide 9: 4.5 Activity cum lesson planner
Item | Description
Purpose | Daily activity plan for entire course duration including class room and on job training
Reference to guidelines | Para 3.2.2.2.3, page – 29
Prerequisite/s | Any time after uploading of Sanction order and 15 days before commencement of training in the particular trade
Time for completion | 15 days before commencement of training in the particular trade
Resource/s | SOP – SF 4.5 A: Activity cum lesson planner (Page no- 70 to 71)
Process owner | PIA OP team

## Slide 10: 4.6 On the job training plan
Item | Description
Purpose | To acclimatise a trainee to actual job conditions
Reference to guidelines | Para 3.2.2.4, page – 29
Prerequisite/s | Should be part of the activity cum lesson planner for the domain. Candidate should have completed the class room training as per activity cum lesson planner
Time for completion | Before placements
Resource/s | SOP – SF 4.6 A: OJT plan for the batch (Page no- 72) SOP – SF 4.6 B: OJT confirmation letter for candidates (Page no- 73) SOP – SF 4.6 C: OJT completion certificate for candidates (Page no- 74) SOP – SF 4.6 D: Verification for OJT (Page no- 75)
Process owner | PIA OP team

## Slide 11: Assessment & Certification (Refer to sub section – 4.7 & 5.4)
Item | Description
Purpose | Outline procedures for assessment and certification of candidates
Reference to guidelines | Para 3.2.2.2.3, page – 29
Prerequisite/s | Admission of a candidate to a batch
Time for completion | Internal assessment: Continuous during the training External assessment: Assessment to be done in the last ten days of training by an agency accredited by NCVT/SSC
Resource/s | SOP – SF 5.4 A: Assessment and certification of candidates, assessment tests and question banks (Page no- 174)
Process owner | PIA OP team

## Slide 12: Assessment & Certification (Refer to sub section – 4.7 & 5.4)
 |  | Has a candidate cleared the assessment test? | 
 |  | Yes | No
Whether a candidate has eligibility criteria prescribed by NCVT/SSC? | Yes | Category 1 Will get the certificate from NCVT/SSC | Category 3 Only course completion certificate from PIA
 | No | Category 2 Will get certificate from assessing body | Category 4 Only course completion certificate from PIA
All category 1 and 2 students who complete 3 months of placement will get certificate from MoRD. |  |  | 

## Slide 13: 4.8 Protocol for managing tablets and electronic content
Item | Description
Purpose | To increase the interest among candidates towards self-learning modules
Reference to guidelines | Para 3.2.2.5, page – 33
Prerequisite/s | Should be part of approved application form
Time for completion | Continuous process
Resource/s | SOP – SF 4.8 A: Daily distribution of Tablets (Page no- 76) SOP – SF 5.2 A: Training Centre inspection form (Page no- 162)
Process owner | PIA OP team

## Slide 14: 4.9 Distance education using live studio based broadcasts
Item | Description
Purpose | To train candidates in topics that are difficult to teach by developing good quality course content that can be standardized and replicated
Reference to guidelines | Para 3.2.2.11, page – 34
Prerequisite/s | Should be part of approved application form and the activity cum lesson planner for the domain
Time for completion | As per the activity cum lesson planner
Resource/s | SOP – SF 4.5 A: Activity cum lesson planner (Page no- 69)
Process owner | PIA OP team

## Slide 15: THANK YOU